## Create and update position deta
Level | Workshop name | Activity ID | 1. What is the Problem? | 2. How often does this happen (Frequency)? | 3. What is the Impact? (Consequence ) | 4. How do you think this problem could be resolved? | ****The following fields are to be completed by IT**** | 5. Reviewed By | 6. Date Reviewed | 7. Implementation Feasibility | 8. ITS Comments | 9. Estimated Implementation Effort (days) | 10. Development Decision - i.e. Project / Quick Win | 11. Estimated Delivery Date | 12. Development Assigned To | 13. Internal IT Comments (Technical) | 14. ITS Status Update
1.2.1.1 Draft Copy | Create and update position details | Overall | One notification for the approvers only, no notifications for the amendments | All positions | No visibility / tracking the status | Additional notifications of job profile amendments
1.2.1.1 Draft Copy | Create and update position details | Overall | Unable to have DOA setup in the system. No reminder functionality | All posts | Delays in the process. Unable to have overview of work in HR. Users do not know who to contact if HR is on leave / absense | Setup DOA. Improved notifications - emails from the system to show progress of a position in the approval cycle
1.2.1.1 Draft Copy | Create and update position details | Overall | SLA work management - HR may geta huge workload if multiple approvals come up at once | Often | Further delays, frustration for staff | Map the activity of the university to eliminate obvious delay reasons and plan accordingly.
1.2.1.1 Draft Copy | Create and update position details | Overall | No clear requirement of what each role in the approval chain needs to see. HESA role missing | All positions | Delays in obtaining the information that has not been displayed. | Clear expectation on what information is needed for each Tier and factoring this in (potentially redesigning / restructuring the existing fields) Drop down needs to be added for HESA
1.2.1.1 Draft Copy | Create and update position details | Overall | As a Hiring Manager / Authoriser - access issues to required information. | Sometimes | Frustration / delays | Understanding the user roles definition to enable correct access to info
1.2.1.1 Draft Copy | Create and update position details | Overall | Multiple approvers for the same tier. A review is required on who needs to approve. Currently the COO and the Head of Department are having to approve current vacancies and acting up allowances. | Not often | Causes delays in progressing | Review of authorisation change, challenge the need of multiple approvers on same tier. Potentially to have COO and Department Head only to approve new roles or roles over a certain grade
1.2.1.1 Draft Copy | Create and update position details | 1 | Duplication of information in the job profile, not clear what information is expected in the sections of the job profiles e.g. What information is required in the APN box? | All posts | Delays in the process due to HR chalenging the information that was put in the job profile | Training + good examples of job profiles Clear guidance & understanding of requirements for all authorising parties
1.2.1.1 Draft Copy | Create and update position details | 1 | Current system allows for ambiguous / incorrect information to be pulled through e.g. if the department is unclear on what the role should be - no clear functionality in i-Grasp to capture the information we need for Ref / HESA | All posts | Quality impact on the data sets. Statutory risk. | Review of existing dropdown, de-clutter, supported by a training piece for users
1.2.1.1 Draft Copy | Create and update position details | 1 | Lack of consistency between job adverts. Lack of generic template for job advert. Inconsistent narative for the job profile descriptions | All posts | Makes it difficult for HR to understand / challenged the content | Definitive generic templates set that is consitent and of good quality
1.2.1.1 Draft Copy | Create and update position details | 3 | No pre-population of standard profiles, need to enter the same information for each new role. | All posts | Wasted time | Set-up of a standard profile template based on a user / department. Something to help the school managers to fill in the information quicker
1.2.1.1 Draft Copy | Create and update position details | 3 | Search facility is poor, difficult to search for previous roles. |  | Delays - No posibility to check against previous profiles, wasted time and effort. | Improved search functionality - challenge product owner
1.2.1.1 Draft Copy | Create and update position details | 3 | Unable to save draft until compulsory information has been filled. Unable to delete draft posts. | All posts | Impact on quality of the data sets. Unnecessary posts remain on "my work" - can cause confusion | Ability to save/delete draft. Difference between save and submit.
1.2.1.1 Draft Copy | Create and update position details | 3 | The button to copy a post creates a new post but doesn't notify the user. Doesn't always work. | All posts | Multiple duplicate posts that can not be deleted unless HR interfers | Functionality needs to be reviewed and raised with the product owner
1.2.1.1 Draft Copy | Create and update position details | 3 | Same person exists on the approval chain - (e.g. School Manager has created the post but also in the approval chain) | Sometimes | Duplication of effort | Better communication with between Schools and HR, so that approval chain can be amended accordingly
1.2.1.1 Draft Copy | Create and update position details | 3 | Unable to sort jobs by date (only by no. of days since it has been created / live) | All posts | Not user friendly, harder to manage workload | Ability to sort by date created.
1.2.1.1 Draft Copy | Create and update position details | 4 | No visibility on whether a job has been graded. | Often | Additional effort to obtain the missing information, delays in the process | Footer to indicate the job has been graded
1.2.1.1 Draft Copy | Create and update position details | 7 | Matching requests on i-Grasp to budget positions on the finance establishment Difficult to reflect evidence of the approval in the system. | Frequently | Delays Job profiles get rejected because budget on the establishment not matching. | A way to link the establishment to i-Grasp - this would work for replacements. Need FTE and post number For additional / changed post - it would be great if FOO / COO would approve first (change tiers around)
1.2.1.1 Draft Copy | Create and update position details | 2 | Lack of transparency / consistency on roles / responsibilities and how it relates to grading a roles | Infrequently | Delay and additional conversations on whether a grade is appropriate. | Comms / templates - joined up approach, input from the Reward & Benefits team
1.2.1.1 Draft Copy | Create and update position details | 8 | Not knowing when final approval will be issued | Often | Unable to plan ahead (panel composition, interview stages) due to the delays in the authorisations | Review of authorisation roles